## Implementation Roadmap
Data Governance Implementation Roadmap Template
Instructions: Replace bracketed placeholders. Duration and % Complete calculate automatically.
Phase | Workstream / Task | Owner | Start Date | End Date | Duration (Days) | Status | % Complete | Dependencies
Phase 1: Initiation | Approve project charter | [Project Manager] | 2026-01-05 | 2026-01-12 | 7 | Not Started | 0% | None
Phase 1: Initiation | Mobilize project team | [Project Manager] | 2026-01-12 | 2026-01-19 | 7 | Not Started | 0% | Charter approval
Phase 1: Initiation | Conduct kickoff workshop | [Project Manager] | 2026-01-19 | 2026-01-21 | 2 | Not Started | 0% | Team mobilized
Phase 2: Design | Define governance processes | [Governance Lead] | 2026-01-22 | 2026-02-12 | 21 | Not Started | 0% | Kickoff complete
Phase 2: Design | Finalize data standards | [Data Steward] | 2026-01-22 | 2026-02-19 | 28 | Not Started | 0% | Kickoff complete
Phase 2: Design | Design technical architecture | [Technical Lead] | 2026-01-29 | 2026-02-19 | 21 | Not Started | 0% | Process design started
Phase 3: Build | Configure governance tooling | [Technical Lead] | 2026-02-20 | 2026-03-20 | 28 | Not Started | 0% | Architecture approved
Phase 3: Build | Onboard pilot domain | [Data Steward] | 2026-03-02 | 2026-03-27 | 25 | Not Started | 0% | Tooling configured
Phase 3: Build | Develop training materials | [Change Mgmt Lead] | 2026-02-20 | 2026-03-13 | 21 | Not Started | 0% | Process design complete
Phase 4: Rollout | Deploy to all business domains | [Project Manager] | 2026-03-30 | 2026-05-08 | 39 | Not Started | 0% | Pilot validated
Phase 4: Rollout | Deliver organization-wide training | [Change Mgmt Lead] | 2026-03-30 | 2026-04-24 | 25 | Not Started | 0% | Training materials ready
Phase 4: Rollout | Activate monitoring dashboards | [Technical Lead] | 2026-04-13 | 2026-04-24 | 11 | Not Started | 0% | Tooling deployed
Phase 5: Stabilization | Transition to operations/BAU | [Governance Lead] | 2026-05-11 | 2026-05-29 | 18 | Not Started | 0% | Rollout complete
Phase 5: Stabilization | Conduct lessons learned review | [Project Manager] | 2026-05-25 | 2026-05-29 | 4 | Not Started | 0% | Transition started
Phase 5: Stabilization | Close project and report to council | [Project Manager] | 2026-05-29 | 2026-06-05 | 7 | Not Started | 0% | Lessons learned complete

## Summary Dashboard
Roadmap Summary
Metric | Value
Total Tasks | 15
Tasks Complete | 0
Tasks At Risk | 0
Tasks Delayed | 0
Average % Complete | 0%
Project Start | 0
Project End | 0
Total Duration (Days) | 0