## Risk Register
Data Governance Implementation – Risk Assessment Matrix
Instructions: Score Likelihood and Impact (1-5). Risk Score and Rating calculate automatically.
Risk ID | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Rating | Mitigation Strategy | Owner | Status | Last Reviewed
R-001 | Stakeholder resistance to new governance processes | Organizational | 3 | 4 | 12 | High | Early engagement and structured change management plan | [Change Mgmt Lead] | Open | 2026-01-15
R-002 | Key resource availability constraints during build phase | Resourcing | 3 | 3 | 9 | Medium | Secure dedicated resource commitments at charter approval | [Project Manager] | Open | 2026-01-15
R-003 | Technical integration delays with source systems | Technical | 3 | 4 | 12 | High | Phased rollout with technical spikes ahead of full build | [Technical Lead] | Open | 2026-01-15
R-004 | Data quality issues surfaced during implementation exceed remediation capacity | Data Quality | 4 | 4 | 16 | Critical | Dedicated remediation workstream with prioritized backlog | [Data Quality Manager] | Open | 2026-01-15
R-005 | Regulatory requirements change mid-implementation | Compliance | 2 | 5 | 10 | High | Maintain regulatory horizon scanning and flexible policy design | [Privacy Officer] | Open | 2026-01-15
R-006 | Budget overrun due to scope creep | Financial | 3 | 3 | 9 | Medium | Formal change control process for all scope additions | [Project Manager] | Open | 2026-01-15
R-007 | Insufficient executive sponsorship visibility | Organizational | 2 | 4 | 8 | Medium | Monthly steering committee reporting cadence | [Executive Sponsor] | Open | 2026-01-15
R-008 | Tooling vendor delivery delays | Technical | 2 | 3 | 6 | Medium | Contractual SLAs and contingency vendor shortlist | [Technical Lead] | Open | 2026-01-15
R-009 | Inadequate training leads to low adoption | Organizational | 3 | 3 | 9 | Medium | Role-based training curriculum with completion tracking | [Change Mgmt Lead] | Open | 2026-01-15
R-010 | Data privacy breach during migration/testing | Security | 2 | 5 | 10 | High | Use masked/synthetic data in non-production environments | [Privacy Officer] | Open | 2026-01-15

## Likelihood-Impact Matrix
Risk Scoring Heat Map (Likelihood x Impact)
Likelihood ↓ / Impact → | 1 | 2 | 3 | 4 | 5
5 | 5 | 10 | 15 | 20 | 25
4 | 4 | 8 | 12 | 16 | 20
3 | 3 | 6 | 9 | 12 | 15
2 | 2 | 4 | 6 | 8 | 10
1 | 1 | 2 | 3 | 4 | 5
Critical (15-25)
High (10-14)
Medium (5-9)
Low (1-4)