# Success Factor Analysis

## Document Information

| Field | Value |
| --- | --- |
| Document Title | Data Governance Implementation — Success Factor Analysis |
| Version | 1.0 |
| Effective Date | [Insert Date] |
| Review Date | [Insert Date - Recommend Annual] |
| Owner | [Data Governance Office] |
| Approved By | [Chief Data Officer] |
| Classification | Internal Use |

## Purpose

This document analyzes the common success factors observed across the Industry Examples in this section, distilling what consistently differentiated high-performing data governance implementations from struggling ones.

## 1. Cross-Industry Success Pattern Summary

| Success Factor | Financial Services | Healthcare | Manufacturing | Retail |
| --- | --- | --- | --- | --- |
| Business (non-IT) co-sponsorship | CRO | CMIO + CPO | COO + VP Supply Chain | CMO + CIO |
| High-visibility pilot domain | Customer master data | Patient master data | Materials master data | Customer 360 |
| Metrics tied to existing reporting cadence | Risk committee | Compliance/quality committee | Operations review | Marketing/merchandising review |
| Early quantifiable win | Reconciliation time -87% | Duplicate rate -81% | Inventory discrepancies -73% | Duplicate profile rate -80% |

## 2. Factor 1: Executive Sponsorship Aligned to Business Pain

Across all four case studies, the most successful programs were sponsored by executives whose function felt the pain most acutely — not generic "data leadership."

Why it matters: Sponsorship aligned to a felt business pain (regulatory risk, patient safety, operational cost, marketing ROI) translates into faster decision-making, budget protection, and credibility with frontline teams.

How to apply it: When identifying your Executive Sponsor (see Data Governance Charter), choose based on who owns the business outcome the pilot domain will improve — not simply who is "interested in data."

## 3. Factor 2: A Single, Well-Chosen Pilot Domain

Every successful case study began with one domain, not an enterprise-wide rollout. The domain was chosen for being both highly visible and genuinely painful to the business.

Why it matters: A focused pilot delivers a believable, demonstrable win in a manageable timeframe (4-8 months), building the credibility needed for expansion.

How to apply it: Use the Current State Assessment and Stakeholder Analysis Template to identify the domain with the highest combination of pain and visibility — not necessarily the easiest to govern technically.

## 4. Factor 3: Embedding Metrics into Existing Governance Forums

Rather than creating new reporting structures, successful programs inserted governance metrics into forums that already had executive attention (risk committees, quality committees, operations reviews).

Why it matters: This avoids "reporting fatigue" and ensures governance progress is seen by the people who already have decision-making authority and influence.

How to apply it: Map your existing executive forums (steering committees, business reviews, risk/compliance meetings) and identify where governance metrics can be added rather than creating a new standalone meeting.

## 5. Factor 4: Pairing Policy With Automation

In every case study, the technical capability (quality rules, identity resolution, lineage tracking) was implemented alongside — not after — the policy. Policies without automated enforcement were consistently identified as a weak point.

Why it matters: Manual-only governance does not scale and tends to degrade once initial enthusiasm fades.

How to apply it: For every new policy or standard, define at least one corresponding automated check using the Data Quality Rules Library or catalog scanning tools before considering the policy "implemented."

## 6. Factor 5: Designing for Sustainability From Day One

Programs that explicitly planned the transition from "project" to "operating capability" (dedicated steward time, ongoing governance forums, recurring training) sustained their gains. Those that treated governance as a finite project saw quality metrics regress within 6-12 months of project closure.

How to apply it: Build the Phase 5: Stabilization activities from the Project Charter Template into your plan from the start, including a named owner for post-project operations.

## 7. Success Factor Checklist

- [ ] Executive sponsor selected based on felt business pain, not generic interest

- [ ] Pilot domain selected using objective pain/visibility criteria

- [ ] Governance metrics embedded into an existing executive forum

- [ ] Every new policy paired with at least one automated quality rule

- [ ] Sustainability/operating model defined before project close

Document Control:

- This is a template document requiring customization for specific organizational needs

- Update as new success patterns are captured through Post-Implementation Reviews

- Pair with Common Implementation Pitfalls for a complementary risk-avoidance view