# 60-Day Implementation Milestones

## Document Information

| Field | Value |
| --- | --- |
| Document Title | [Organization Name] Data Governance — 60-Day Implementation Milestones |
| Version | 1.0 |
| Effective Date | [Insert Date] |
| Review Date | [Insert Date - Recommend Annual] |
| Owner | [Project Manager] |
| Approved By | [Chief Data Officer] |
| Classification | Internal Use |

## Purpose

This document defines the milestones expected between Day 31 and Day 60 of the data governance program — the period focused on building out the pilot domain and proving early value. It follows directly from the First 30 Days Checklist.

## Days 31-40: Pilot Domain Build-Out

- [ ] Pilot domain source systems registered in the data catalog (Data_Catalog_Setup_Scripts.sql)

- [ ] Technical metadata extracted and loaded (Metadata_Extraction_Tools.py)

- [ ] Initial Critical Data Elements identified for the pilot domain

- [ ] Business definitions drafted for Critical Data Elements

- [ ] Data Classification Scheme applied to pilot domain assets

## Days 41-50: Quality and Lineage Foundations

- [ ] Initial data quality rules implemented for pilot domain CDEs (Data_Quality_Rules_Library.py)

- [ ] Baseline quality scorecard generated for the pilot domain

- [ ] Lineage documented for at least one critical end-to-end data flow (source → warehouse → report)

- [ ] Data Issue Resolution Process activated for the pilot domain — issue tracker live

- [ ] Pilot domain Data Stewards trained on Modules 1-3 of the Data Steward Training Curriculum

## Days 51-60: Validate and Prepare to Scale

- [ ] Pilot domain quality scorecard reviewed with Business Data Steward and Council

- [ ] At least one tangible "before/after" comparison documented (e.g., duplicate rate reduction, faster reconciliation)

- [ ] Lessons learned captured via a Post-Implementation Review for the pilot build-out

- [ ] Expansion domain(s) for the next phase identified and prioritized

- [ ] Change Management Toolkit activities (communications, training plan) prepared for expansion phase

- [ ] 60-day status report delivered to the Data Governance Council (Monthly Governance Report Template)

## Milestone Summary Table

| Milestone | Target Day | Owner | Dependency |
| --- | --- | --- | --- |
| Pilot domain assets registered in catalog | Day 35 | [Technical Data Steward] | Source system access provisioned |
| Critical Data Elements identified | Day 38 | [Business Data Steward] | Asset registration complete |
| Initial quality rules live | Day 45 | [Technical Data Steward] | CDEs identified |
| End-to-end lineage documented (1 flow) | Day 48 | [Technical Data Steward] | Quality rules live |
| Issue tracker activated | Day 50 | [Data Governance Office] | None |
| Steward training (Modules 1-3) complete | Day 52 | [Change Management Lead] | Stewards identified |
| Pilot results reviewed with Council | Day 58 | [Project Manager] | Scorecard available |
| 60-day status report delivered | Day 60 | [Project Manager] | All above complete |

## Risk Watch List for This Phase

- Source system access delays — engage IT/system owners early; this is the most common Day 31-60 bottleneck

- Steward bandwidth — confirm protected time commitments were secured during charter approval

- Scope creep — keep the pilot tightly scoped; resist requests to expand before proving value (see Common Implementation Pitfalls)

## Quick Reference: Key Templates Used This Phase

| Need | Template |
| --- | --- |
| Catalog and metadata setup | Data_Catalog_Setup_Scripts.sql, Metadata_Extraction_Tools.py |
| Quality rule implementation | Data_Quality_Rules_Library.py |
| Lineage documentation | Data_Lineage_Mapping_Templates.xlsx, Data_Lineage_Discovery_Tools.py |
| Issue tracking | Data_Issue_Resolution_Process.md |
| Steward training | Data_Steward_Training_Curriculum.pptx |
| Status reporting | Monthly_Governance_Report_Template.md |

Document Control:

- This is a template document requiring customization for specific organizational needs

- Sections in [brackets] require organization-specific information

- Pair with First_30_Days_Checklist.md and 90_Day_Success_Metrics.xlsx for the full first-quarter plan