## 90-Day Success Metrics
90-Day Success Metrics Tracker
Instructions: Set targets during program planning; update Actual columns at Day 30/60/90 checkpoints.
Metric | Baseline (Day 0) | Day 30 Target | Day 30 Actual | Day 60 Target | Day 60 Actual | Day 90 Target
Governance structure established (Charter, Council) | No | Yes |  | Yes |  | Yes
Pilot domain selected and scoped | No | Yes |  | Yes |  | Yes
Pilot domain assets registered in catalog | 0 | 0 |  | 25 |  | 40
Critical Data Elements identified (pilot domain) | 0 | 0 |  | 10 |  | 20
Data quality rules implemented (pilot domain) | 0 | 0 |  | 8 |  | 20
Average pilot domain quality score (%) | N/A | N/A |  | 70 |  | 85
Data Stewards trained (Modules 1-3) | 0 | 0 |  | 2 |  | 4
End-to-end lineage flows documented | 0 | 0 |  | 1 |  | 3
Data issues logged and triaged | 0 | 0 |  | 5 |  | 15
Stakeholder awareness survey completion (%) | 0 | 0 |  | 40 |  | 70

## Day 90 Readiness Scorecard
Day 90 Readiness Scorecard
Score each readiness area 1 (Not Ready) to 5 (Fully Ready) at the Day 90 checkpoint.
Readiness Area | Score (1-5) | Status | Notes
Governance structure operating independently | 3 | Mostly Ready
Pilot domain fully governed (catalog, quality, lineage) | 3 | Mostly Ready
Demonstrated quantifiable value (before/after comparison) | 3 | Mostly Ready
Data Stewards confident and active in their roles | 3 | Mostly Ready
Expansion domain(s) identified and roadmap approved | 3 | Mostly Ready
Sustainability plan in place (ongoing ownership, budget) | 3 | Mostly Ready
Overall Readiness Score | 3