# First 30 Days Checklist

## Document Information

| Field | Value |
| --- | --- |
| Document Title | [Organization Name] Data Governance — First 30 Days Checklist |
| Version | 1.0 |
| Effective Date | [Insert Date] |
| Review Date | [Insert Date - Recommend Annual] |
| Owner | [Project Manager / Chief Data Officer] |
| Approved By | [Executive Sponsor] |
| Classification | Internal Use |

## Purpose

This checklist guides the first 30 days of a data governance program launch — the foundation-setting period between executive approval and the start of pilot domain work. It complements the Project Charter Template and Implementation Roadmap.

## Week 1: Mobilize

- [ ] Project Charter formally approved and signed by Executive Sponsor

- [ ] Data Governance Council members confirmed and first meeting scheduled

- [ ] Chief Data Officer (or program lead) role formally assigned

- [ ] Core Data Governance Office team identified (Project Manager, Governance Analyst(s))

- [ ] Project workspace/repository set up (using this template library as the starting point)

- [ ] Kickoff workshop scheduled with key stakeholders

## Week 2: Assess and Align

- [ ] Current State Assessment completed or reviewed if already done

- [ ] Data Governance Maturity Assessment baseline captured

- [ ] Stakeholder Analysis Template completed to map influence/interest

- [ ] Pilot domain candidates identified using pain/visibility criteria (see Success Factor Analysis)

- [ ] Budget and resource allocation confirmed against the Project Charter

## Week 3: Establish the Foundation

- [ ] Data Governance Charter finalized and distributed

- [ ] Initial Data Classification Scheme drafted for stakeholder review

- [ ] RACI Matrix completed for governance roles

- [ ] Draft Data Stewardship Policy circulated for feedback

- [ ] Communication Plan drafted (Stakeholder Communication Plan template)

- [ ] Pilot domain formally selected and confirmed with Data Governance Council

## Week 4: Prepare for Pilot Launch

- [ ] Pilot domain Business and Technical Data Stewards identified and approached

- [ ] Initial source systems for the pilot domain inventoried

- [ ] Data Catalog Setup Scripts reviewed and environment provisioned (or platform-specific setup guide selected from Section 08)

- [ ] First Data Governance Council meeting held — charter, roadmap, and pilot scope approved

- [ ] 30-day kickoff communication sent to the broader organization

- [ ] 60-Day Implementation Milestones plan finalized

## End-of-30-Days Readiness Check

Before moving into the 60-day phase, confirm:

- [ ] Governance structure (Council, Office, initial Stewards) is staffed and meeting

- [ ] Charter, Classification Scheme draft, and Stewardship Policy draft exist

- [ ] Pilot domain is selected, scoped, and stakeholders are engaged

- [ ] Baseline metrics are captured for later comparison

- [ ] Communication plan is active and the organization knows the program has launched

If any of the above are incomplete, address them before proceeding — a shaky foundation compounds problems later (see Common Implementation Pitfalls).

## Quick Reference: Key Templates Used This Phase

| Need | Template |
| --- | --- |
| Formal program authorization | Project Charter Template |
| Governance structure | Data Governance Charter Template, RACI Matrix Templates |
| Baseline measurement | Data Governance Maturity Assessment, Current State Assessment Guide |
| Stakeholder planning | Stakeholder Analysis Template, Stakeholder Communication Plan |
| Pilot domain scoping | Implementation Roadmap Template |

Document Control:

- This is a template document requiring customization for specific organizational needs

- Sections in [brackets] require organization-specific information

- Pair with 60_Day_Implementation_Milestones.md and 90_Day_Success_Metrics.xlsx for the full first-quarter plan